## Remediation Tracker
Finding ID | Description | Severity | Owner | Due Date | Status
F-001 | Missing MFA on admin accounts | High | IT Security | 2026-06-01 | In Progress
F-002 | Outdated incident response plan | Medium | Security Analyst | 2026-06-15 | Open
F-003 | Incomplete access reviews | High | IT Manager | 2026-06-01 | Overdue
F-004 | Backup testing not documented | Medium | IT Ops | 2026-06-15 | Open
F-005 | Weak password policy | Low | HR/IT | 2026-06-10 | Closed